## README
Section | Content
Demo scenario | Hong Kong specialist subcontractor working on a building E&M / fit-out package.
Report type | Internal Monthly Project Health Report for Director, PM, and QS review.
Reporting month | April 2026; report-as-of date 2026-04-30.
Teaching objective | Show how Codex / AI can validate a multi-sheet Excel data pack, calculate KPIs, generate charts, draft user-specific narratives, render Markdown / HTML / PDF, and stop for human review.
Core workflow | Load workbook -> validate schema, formulas and cross-links -> recompute KPI/RAG -> generate charts -> render Markdown/HTML/PDF draft -> prepare email draft -> stop at human review gates (PM / QS / Director) before any send.
Deliberate data issues | Missing Actual % in Area Progress; inconsistent RFI/submission status labels; overdue RFI; missing forecast delivery date; commercial raw source issue marker; overdue safety/quality actions.
Important teaching point | This data pack is fictitious and anonymized. It is a teaching-grade demo input, not a production-grade report system.
How to use in Codex | Ask Codex to inspect sheets first, propose a plan, then generate a script to read this workbook and output Markdown/HTML/PDF report drafts with a data-quality log.

## 00_Project_Profile
Field | Value | Owner | Data_Classification | Notes
Project_ID | HKC-EM-001 | PM / Admin | CONTROL | Key used across sheets
Project_Name | Harbourview Commercial Tower - E&M & Fit-out Interface Package | PM / Admin | CONTROL | Fictitious teaching project
Contract_No | SC-2026-EM-01 | PM / Admin | CONTROL
Subcontractor | Wan Tsun E&M Engineering Limited | PM / Admin | CONTROL | Fictitious company
Client_or_Main_Contractor | Harbour Gate Construction Company Limited | PM / Admin | CONTROL | Fictitious company
Reporting_Period_Start | 2026-04-01 | PM / Admin | CONTROL
Reporting_Period_End | 2026-04-30 | PM / Admin | CONTROL | Report-as-of date
Project_Director | Mr. Chan | PM / Admin | CONTROL | Director dashboard reviewer
Project_Manager | Ms. Lee | PM / Admin | CONTROL | Final report owner
QS_Commercial_Manager | Mr. Wong | QS / Commercial | CONTROL | Commercial section owner
Construction_Manager | Mr. Ho | Construction | CONTROL | Progress section owner
Planning_Manager | Ms. Ng | Planner | CONTROL | Programme section owner
Technical_Manager | Mr. Lau | Technical | CONTROL | Submission/RFI owner
Safety_Officer | Ms. Tam | Safety | CONTROL | Safety owner
QAQC_Manager | Mr. Ip | QA/QC | CONTROL | Quality owner
Contract_Value_HKD_M | 68.5 | QS / Commercial | CONTROL | Original net contract sum
Baseline_Completion_Date | 2026-12-15 | Planner | CONTROL
Current_Forecast_Completion_Date | 2026-12-28 | Planner | CONTROL | 13-day movement
Report_Version | Draft v0.1 | PM / Admin | GO | For workshop only

## 01_Area_Progress
Progress_ID | Zone_Area | Level | Trade | Activity | Planned_%_This_Month | Actual_%_This_Month | Variance_% | Planned_Qty | Actual_Qty | Unit | RAG_Status | Delay_Variance_Reason | Impact | Action | Owner | Due_Date | Photo_Refs | Linked_RFI | Linked_Milestone | Data_Quality_Note
PRG-001 | Tower A | L10-L12 | Electrical | Cable tray installation | 70% | 68% | -2% | 1200 | 1165 | m | Green | Minor access coordination | No material impact | Monitor daily progress | Section Engineer | 2026-05-06 | P-001,P-002 |  | M-003
PRG-002 | Tower A | L13-L15 | MVAC | Ductwork installation | 72% | 63% | -9% | 950 | 810 | m | Yellow | Access conflict with ceiling framing | May affect ceiling closure sequence | Resequence with fit-out team | Construction Manager | 2026-05-08 | P-011,P-012 | RFI-034 | M-006
PRG-003 | Zone B | L16-L18 | MVAC | E&M first fix | 70% | 58% | -12% | 1100 | 910 | m | Red | Design clash: duct route vs structural beam | Potential delay to ceiling closure and inspection | Escalate RFI-034; prepare alternative route sketch | PM / Technical Manager | 2026-05-05 | P-042,P-043 | RFI-034 | M-006
PRG-004 | Podium | L1-L2 | Fire Services | Sprinkler pipework | 85% | 80% | -5% | 780 | 740 | m | Green | Manpower slightly below plan | Low impact if recovered next week | Add 4-person crew for two evenings | Construction Manager | 2026-05-07 | P-021 |  | M-004
PRG-005 | Plant Room | B2 | MVAC | AHU plinth and builder's work readiness | 50% | 45% | -5% | 8 | 7 | no. | Yellow | AHU delivery forecast slip | Plant room installation may move by 9 days | Supplier recovery meeting | Procurement Manager | 2026-05-06 | P-031 | MAT-021 | M-012
PRG-006 | Tower A | L20-L23 | Electrical | Small power containment | 60% |  |  | 620 |  | m | Data Gap | Data not updated by section team | AI must not infer progress | Request actual progress update before final report | Section Engineer | 2026-05-03 |  |  | M-009 | Missing Actual % and Actual Qty
PRG-007 | Tower A | L08-L09 | ELV | ELV trunking | 55% | 60% | 5% | 480 | 520 | m | Green | Ahead due to clear access | Positive buffer | Keep crew allocation | ELV Engineer | 2026-05-04 | P-015 |  | M-002
PRG-008 | Back of House | B1 | Plumbing | Drainage pipework | 65% | 62% | -3% | 360 | 345 | m | Green | Minor coordination with builders work | No critical impact | Monitor inspection readiness | Site Engineer | 2026-05-09 | P-018 |  | M-005
PRG-009 | Retail | G/F | Fit-out Interface | Ceiling closure readiness | 40% | 32% | -8% | 22 | 18 | bay | Yellow | Dependent on unresolved E&M clash | Risk to fit-out handover sequence | Hold interface meeting | PM | 2026-05-07 | P-050 | RFI-039 | M-013
PRG-010 | External Yard | G/F | Builder's Works | Openings and sleeves | 45% | 48% | 3% | 44 | 47 | no. | Green | Ahead of plan | Positive buffer | Maintain QA record | Site Engineer | 2026-05-02 | P-061 |  | M-007
PRG-011 | Tower A | L04-L06 | T&C | Pre-T&C checks | 20% | 18% | -2% | 30 | 27 | check | Green | Access to DB rooms partial | Low impact currently | Confirm room handover dates | T&C Manager | 2026-05-15 | P-071 |  | M-014
PRG-012 | Tower A | L16-L18 | Fit-out Interface | Ceiling closure | 55% | 40% | -15% | 28 | 20 | bay | Red | Blocked by MVAC first fix delay | Critical interface risk | Approve recovery shift after RFI escalation | Project Director | 2026-05-07 | P-080 | RFI-034 | M-013

## 02_Programme_Milestones
Milestone_ID | Milestone_Name | Baseline_Date | Current_Forecast_Date | Variance_Days | Critical_Path | Linked_Progress_Item | Linked_RFI_Submission | Reason | Recovery_Action | Owner | RAG_Status | Review_Note
M-001 | Mobilisation completed | 2026-01-15 | 2026-01-15 | 0 | No |  |  | Completed | N/A | PM | Green | Historical completed milestone
M-002 | ELV trunking L08-L09 complete | 2026-04-28 | 2026-04-26 | -2 | No | PRG-007 |  | Ahead of plan | Keep resource stable | ELV Engineer | Green | Positive progress
M-003 | Cable tray L10-L12 complete | 2026-05-05 | 2026-05-06 | 1 | No | PRG-001 |  | Minor access coordination | Daily follow-up | Section Engineer | Yellow | Low risk
M-004 | Sprinkler pipework Podium L1-L2 complete | 2026-05-08 | 2026-05-10 | 2 | No | PRG-004 |  | Manpower below plan | Add evening crew | Construction Manager | Yellow | Monitor
M-005 | Drainage pipework B1 complete | 2026-05-12 | 2026-05-13 | 1 | No | PRG-008 |  | Inspection coordination | Confirm inspection booking | Site Engineer | Yellow | Monitor
M-006 | Complete E&M first fix Zone B | 2026-05-15 | 2026-05-25 | 10 | Yes | PRG-003 | RFI-034 | RFI-034 pending; duct/beam clash | Escalate to consultant and issue recovery sequence | PM / Planner | Red | Critical path impact
M-007 | Builder's works openings complete | 2026-05-20 | 2026-05-18 | -2 | No | PRG-010 |  | Ahead | Maintain QA records | Site Engineer | Green | Positive
M-009 | Small power containment L20-L23 complete | 2026-05-22 | 2026-05-24 | 2 | No | PRG-006 |  | Progress data missing | Request update; verify on site | Section Engineer | Yellow | Data gap impacts confidence
M-012 | AHU delivery / plant room installation readiness | 2026-06-01 | 2026-06-10 | 9 | Yes | PRG-005 | MAT-021 | Forecast delivery slip | Supplier recovery meeting | Procurement Manager | Red | Potential critical plant room delay
M-013 | Ceiling closure Tower A L16-L18 | 2026-05-25 | 2026-06-08 | 14 | Yes | PRG-012 | RFI-034 | Blocked by first fix delay | Approve recovery shift after design response | Project Director | Red | Director decision required
M-014 | Pre-T&C checks L04-L06 complete | 2026-06-15 | 2026-06-17 | 2 | No | PRG-011 |  | Room access partial | Confirm room handover dates | T&C Manager | Yellow | Monitor

## 03_Submission_RFI
Record_ID | Type | Package_Trade | Description | Date_Raised_Submitted | Response_Due_Date | Response_Received_Date | Days_Open_Overdue | Status_Raw | Status_Normalized | Revision | Linked_Area_Activity | Linked_Milestone | Programme_Impact_Days | Commercial_Impact | Responsible_Person | Escalation_Required | RAG_Status | Data_Quality_Note
SUB-081 | Shop Drawing | Electrical | Cable tray layout L10-L12 | 2026-03-20 | 2026-04-05 | 2026-04-03 | -2 | Approved | Approved | Rev C | PRG-001 | M-003 | 0 | None | Technical Manager | No | Green
SUB-082 | Material Submission | Fire Services | Sprinkler head sample | 2026-03-25 | 2026-04-10 | 2026-04-12 | 2 | approved | Approved | Rev B | PRG-004 | M-004 | 2 | Low | Design Coordinator | No | Yellow | Status lower-case intentionally
SUB-088 | Shop Drawing | MVAC | AHU plant room layout | 2026-04-05 | 2026-04-22 |  | 8 | Pending approval | Pending | Rev B | PRG-005 | M-012 | 5 | Potential VO if plant layout changed | Technical Manager | Yes | Yellow
RFI-034 | RFI | MVAC | Clash between duct route and structural beam | 2026-04-10 | 2026-04-24 |  | 6 | OPEN | Open | N/A | PRG-003 / PRG-012 | M-006 / M-013 | 10 | Potential VO / EOT support | PM / Engineer | Yes | Red | Critical teaching example
RFI-035 | RFI | Electrical | DB room access handover clarification | 2026-04-12 | 2026-04-26 | 2026-04-29 | 3 | Answered | Answered | N/A | PRG-011 | M-014 | 2 | None | Project Engineer | No | Yellow
SUB-089 | Method Statement | General | Night / weekend recovery work method | 2026-04-18 | 2026-05-02 |  | -2 | PENDING | Pending | Rev A | PRG-012 | M-013 | 7 | Potential acceleration cost | PM | Yes | Yellow | Status upper-case intentionally
RFI-039 | RFI | Fit-out Interface | Ceiling closure sequence for G/F retail area | 2026-04-20 | 2026-04-28 |  | 2 | open | Open | N/A | PRG-009 | M-013 | 5 | Possible prolongation risk | Fit-out Coordinator | No | Yellow | Status lower-case intentionally
SUB-091 | Material Submission | MVAC | AHU delivery documents | 2026-04-21 | 2026-05-05 |  | -5 | Not Yet Submitted | Not Yet Submitted | Rev 0 | PRG-005 | M-012 | 9 | Long-lead item risk | Procurement Manager | Yes | Yellow | Submission not yet issued
SUB-092 | Shop Drawing | Plumbing | B1 drainage as-built mark-up | 2026-04-22 | 2026-05-06 |  | -6 | Pending | Pending | Rev A | PRG-008 | M-005 | 0 | None | Site Engineer | No | Green
RFI-041 | RFI | Builder's Works | Opening dimension confirmation | 2026-04-25 |  |  |  | Open | Open | N/A | PRG-010 | M-007 | 0 | None | Site Engineer | Yes | Data Gap | Missing response due date

## 04_Procurement
Item_ID | Item_Description | Package | Required_Onsite_Date | Approval_Status | PO_Status | Supplier | Forecast_Delivery_Date | Variance_Days | Linked_Milestone | Risk_Status | Action | Owner | Data_Quality_Note
MAT-001 | Cable trays L10-L15 | Electrical | 2026-04-25 | Approved | Issued | Cheong Lik Metalworks Ltd | 2026-04-22 | -3 | M-003 | Green | Delivered; monitor installation | Procurement Manager
MAT-008 | Sprinkler pipe materials | Fire Services | 2026-05-01 | Approved | Issued | Firecrest FS Supplies Ltd | 2026-05-02 | 1 | M-004 | Yellow | Confirm delivery slot | Procurement Manager
MAT-011 | ELV trunking | ELV | 2026-04-20 | Approved | Issued | Trunkline ELV Systems Ltd | 2026-04-18 | -2 | M-002 | Green | Delivered | ELV Engineer
MAT-021 | AHU Unit | MVAC | 2026-06-01 | Approved | Issued | Coolrise Air Systems (HK) Ltd | 2026-06-10 | 9 | M-012 | Yellow | Supplier recovery meeting | Procurement Manager | Critical long-lead item
MAT-024 | Fire-rated access panels | Fit-out Interface | 2026-05-20 | Pending Approval | Not Issued | Panelform Building Products Ltd | 2026-05-30 | 10 | M-013 | Red | Expedite approval and PO | Technical Manager | Approval and PO not completed
MAT-026 | DB room accessories | Electrical | 2026-05-28 | Approved | Issued | Voltcrest Electrical Supplies Ltd |  |  | M-014 | Data Gap | Request forecast delivery date | Procurement Manager | Missing Forecast Delivery Date
MAT-032 | Chilled water valves | MVAC | 2026-06-15 | Approved | Issued | Hydroseal Valve & Fittings Ltd | 2026-06-18 | 3 | M-012 | Yellow | Monitor factory schedule | Procurement Manager
MAT-040 | Drainage pipe supports | Plumbing | 2026-05-08 | Approved | Issued | Steadfix Support Systems Ltd | 2026-05-08 | 0 | M-005 | Green | No action | Site Engineer
MAT-041 | Fire dampers Zone B risers | MVAC | 2026-05-25 | Approved | Issued | Flowvent Air Products Ltd | 2026-05-22 | -3 | M-006 | Green | Delivery on track; hold at site store | Procurement Manager
MAT-045 | LED luminaires L20-L23 | Electrical | 2026-06-05 | Approved | Issued | Brightform Lighting Ltd | 2026-06-05 | 0 | M-009 | Green | Confirm delivery booking with main contractor hoist | Procurement Manager

## 05_Safety_Quality
Record_ID | Category | Metric_or_Issue | Count_Value | Unit | Target | Actual_Result | Status | Area | Description | Action_Required | Owner | Due_Date | Days_Overdue | RAG_Status | Evidence_Ref | Data_Quality_Note
SQ-001 | Safety | Reportable accident | 0 | case | 0 | 0 case | Closed | Project-wide | No reportable accident in April | Continue safety briefing | Safety Officer | 2026-04-30 | 0 | Green | S-APR-001
SQ-002 | Safety | Near miss | 2 | case | 0 | 2 cases | Open | Tower A | Two near-miss observations related to access and lifting zone | Review lifting/access controls | Safety Officer | 2026-05-03 | -3 | Yellow | S-APR-014
SQ-003 | Safety | Overdue safety actions | 3 | action | 0 | 3 overdue | Open | Project-wide | Three corrective actions remain overdue | Close overdue actions before report finalization | Safety Officer | 2026-04-28 | 2 | Yellow | S-APR-022
SQ-004 | Safety | High-risk outstanding item | 1 | item | 0 | 1 item | Open | Tower A L16 | Work-at-height edge protection observation remains open | Immediate closure required | Safety Officer | 2026-04-27 | 3 | Red | S-APR-027
SQ-005 | Quality | Open NCR | 1 | case | 0 | 1 open | Open | Tower A L12 | Cable tray support spacing not compliant | Rectify and re-inspect | QA/QC Manager | 2026-04-26 | 4 | Yellow | NCR-009
SQ-006 | Quality | Inspection pass rate | 0.88 | rate | 0.9 | 88% | Open | Project-wide | Inspection pass rate below target by 2% | Review repeated inspection failures | QA/QC Manager | 2026-05-07 | -7 | Yellow | QC-APR-002
SQ-007 | Environmental | Complaint | 0 | case | 0 | 0 case | Closed | Project-wide | No environmental complaint | Maintain monitoring | Environmental Officer | 2026-04-30 | 0 | Green | ENV-APR-001
SQ-008 | Quality | Missing inspection due date | 1 | record | 0 | 1 record | Open | Plant Room B2 | Inspection record has no agreed rectification due date | Confirm due date with QA/QC | Site Engineer |  |  | Data Gap | QC-APR-019 | Missing Due Date

## 06_Commercial_Cost
Reporting_Month | Project_ID | Original_Net_Contract_Sum_HKD_M | Contract_Sum_with_VO_HKD_M | Accounted_VO_Income_HKD_M | Accounted_VO_Cost_HKD_M | VO_Net_HKD_M | Obj_GP_HKD_M | Obj_GP_% | Current_GP_HKD_M | Current_GP_% | GP_vs_Objective_HKD_M | GP_vs_Objective_% | Payment_Received_HKD_M | Actual_Expenditure_HKD_M | Nett_Cashflow_HKD_M | Cost_Certified_HKD_M | Cost_Certified_% | Commitment_HKD_M | Commitment_% | Risk_Exposure_HKD_M | Performance_Score_0_to_10 | RAG_Status | Raw_Source_Issue | Data_Quality_Note
2026-01-31 | HKC-EM-001 | 68.5 | 69.4 | 1.05 | 0.25 | 0.8 | 3.42 | 5% | 3.48 | 5.014% | 0.06 | 0.01441% | 38.6 | 38.2 | 0.4 | 39.8 | 57.35% | 58.4 | 84.15% | 0.3 | 8 | Green
2026-02-28 | HKC-EM-001 | 68.5 | 69.9 | 1.75 | 0.75 | 1 | 3.42 | 5% | 3.36 | 4.807% | -0.06 | -0.1931% | 41.9 | 41.5 | 0.4 | 43.1 | 61.66% | 61.2 | 87.55% | 0.4 | 7 | Yellow
2026-03-31 | HKC-EM-001 | 68.5 | 70.5 | 2.55 | 1.25 | 1.3 | 3.42 | 5% | 3.2 | 4.539% | -0.22 | -0.461% | 45.8 | 45.3 | 0.5 | 47.4 | 67.23% | 64.8 | 91.91% | 0.6 | 7 | Yellow |  | Previous month baseline
2026-04-30 | HKC-EM-001 | 68.5 | 71.2 | 3.1 | 1.6 | 1.5 | 3.42 | 5% | 3.05 | 4.284% | -0.37 | -0.7163% | 48.2 | 48 | 0.2 | 49.5 | 69.52% | 66.9 | 93.96% | 1.2 | 6 | Yellow | Original QS matrix had duplicate cashflow labels and a simulated formula error marker FORMULA_ERROR_DIV0 in a non-official check column; this sheet uses official KPI fields only. | Current month for demo

## 07_Risk_Action_Decision
Issue_ID | Category | Linked_Records | Description | Impact | Decision_Required | Recommendation | Owner | Due_Date | Status | RAG_Status | Human_Review_Gate | Notes
ISS-001 | Submission/RFI | RFI-034 / PRG-003 / M-006 | Overdue RFI-034 blocking Zone B duct installation | Potential 10-day delay to E&M first fix and ceiling closure | Escalate to main contractor / consultant | Issue formal escalation and request decision meeting | PM | 2026-05-05 | Open | Red | PM + Technical Manager | Core demo issue
ISS-002 | Programme Recovery | PRG-012 / M-013 | Ceiling closure Tower A L16-L18 forecast 14 days late | Critical interface risk with fit-out team | Approve weekend recovery shift | Approve controlled weekend work after safety method review | Project Director | 2026-05-07 | Open | Red | Project Director | Director decision required
ISS-003 | Procurement | MAT-021 / PRG-005 / M-012 | AHU delivery forecast 9 days late | Potential plant room installation delay | Supplier recovery plan required | Hold supplier recovery meeting and confirm delivery options | Procurement Manager | 2026-05-06 | Open | Yellow | PM + Procurement Manager
ISS-004 | Commercial | 06_Commercial_Cost | Current GP below objective by HK$0.37M | Margin erosion risk | Review VO/cost recovery strategy | QS to review VO pricing and commitment exposure | QS / Commercial Manager | 2026-05-10 | Open | Yellow | QS + Director
ISS-005 | Safety | SQ-004 | High-risk work-at-height observation remains open | Safety risk and potential stoppage | Immediate closure required | Close item and provide evidence photo | Safety Officer | 2026-05-02 | Open | Red | Safety Officer
ISS-006 | Quality | NCR-009 / SQ-005 | Cable tray support spacing NCR remains open | May affect inspection and rework cost | Rectification approval | Rectify and re-inspect Tower A L12 | QA/QC Manager | 2026-05-04 | Open | Yellow | QA/QC Manager
ISS-007 | Data Quality | PRG-006 | Actual progress missing for L20-L23 small power containment | Report confidence reduced | Require progress update before final report | Section engineer to update actual % and quantity | Section Engineer | 2026-05-03 | Open | Data Gap | PM | Use to demo AI not guessing
ISS-008 | Data Quality | RFI / Submission status fields | Status labels are inconsistent: approved, OPEN, pending, PENDING | Automation may misclassify status | Normalize status values | Codex script should standardize statuses and log issue | Technical Manager | 2026-05-03 | Open | Yellow | Technical Manager | Self-healing demo

## 08_Metric_Dictionary
Metric_ID | Metric_Name | Management_Question | Source_Sheet | Source_Fields | Formula_or_Logic | Owner | Primary_Audience | RAG_Rule | Evidence_Required
PRO-001 | Progress variance by area | Which areas are behind plan? | 01_Area_Progress | Planned_%_This_Month; Actual_%_This_Month | Actual % minus Planned % | Construction Manager | PM / Director | Red <= -10%; Yellow <= -5%; Green otherwise | Area progress table + photos
PRO-002 | Data gap in progress | Which progress rows cannot be trusted? | 01_Area_Progress | Actual_%_This_Month; Actual_Qty | Flag missing actual progress or actual quantity | PM | PM | Data Gap if required actual field missing | Section update
SCH-001 | Milestone variance days | Is the programme delayed? | 02_Programme_Milestones | Baseline_Date; Current_Forecast_Date | Current forecast minus baseline date | Planner | Director / PM | Red if critical path delay >7 days; Yellow if delay >0 | Programme update
RFI-001 | Overdue RFI / submission days | What approvals are blocking work? | 03_Submission_RFI | Response_Due_Date; Response_Received_Date | If no response, report-as-of date minus due date | Technical Manager | PM | Red if >14 days or impact >=10 days; Yellow if overdue | RFI register
RFI-002 | Status normalization quality | Can AI classify submission status reliably? | 03_Submission_RFI | Status_Raw | Normalize casing and synonyms | Technical Manager | PM / Codex demo | Yellow if inconsistent status labels found | Raw status field
PRC-001 | Procurement delivery variance | Are long-lead items late? | 04_Procurement | Required_Onsite_Date; Forecast_Delivery_Date | Forecast delivery minus required date | Procurement Manager | PM / Director | Data Gap if no forecast; Yellow if late; Red if approval/PO not completed | Procurement tracker
SQE-001 | Safety exceptions | Any safety red flags? | 05_Safety_Quality | RAG_Status; Days_Overdue | Count open Red/Yellow safety records | Safety Officer | Director / PM | Red if high-risk outstanding item open | Safety log
QUA-001 | Open NCR / quality exception | Any quality issue affecting handover? | 05_Safety_Quality | Category; RAG_Status | Count open quality Yellow/Red records | QA/QC Manager | PM | Yellow if open NCR exists | NCR / inspection record
COM-001 | Current GP % | Is the project profitable? | 06_Commercial_Cost | Current_GP_HKD_M; Contract_Sum_with_VO_HKD_M | Current GP divided by contract sum with VO | QS / Commercial Manager | Director / QS | Yellow if below objective GP; Red if materially below | Commercial matrix
COM-002 | GP vs objective | Is margin above or below target? | 06_Commercial_Cost | Current_GP_HKD_M; Obj_GP_HKD_M | Current GP minus objective GP | QS / Commercial Manager | Director / QS | Yellow if below objective; Red if below by > HK$0.5M | Commercial matrix
COM-003 | VO net position | Are VOs adding value? | 06_Commercial_Cost | Accounted_VO_Income_HKD_M; Accounted_VO_Cost_HKD_M | VO income minus VO cost | QS / Commercial Manager | QS / Director | Yellow if VO net reduces month-on-month | VO register
COM-004 | Net cashflow | Is the project consuming cash? | 06_Commercial_Cost | Payment_Received_HKD_M; Actual_Expenditure_HKD_M | Payment received minus actual expenditure | QS / Finance | Director / Finance | Red if negative; Yellow if near neutral | Payment/cost records
COM-005 | Commitment % | How much of budget is already committed? | 06_Commercial_Cost | Commitment_HKD_M; Contract_Sum_with_VO_HKD_M | Commitment divided by contract sum with VO | QS / Commercial Manager | Director / PM | Yellow if >90%; Red if >100% | PO/WO/VO records
ACT-001 | Decision count | What does management need to decide? | 07_Risk_Action_Decision | Decision_Required; RAG_Status | Count open Red/Yellow decisions | PM | Director | Red if open Red decision exists | Decision log
DQ-001 | Report confidence | Can the report be issued without manual checks? | All sheets | Data_Quality_Note; Data Gap RAG | Count unresolved data gaps and source issues | PM | All users | Data Gap if critical data missing | Data quality log

## 09_Review_Gates
Review_Gate_ID | Report_Section | Reviewer | What_To_Check | Decision | Stop_Condition | Output_Status
RG-001 | Data Quality Log | PM / Project Admin | Missing fields, duplicated labels, date errors, formula issue markers | Accept / request correction | Critical Data Gap in progress, RFI, commercial metrics | Draft only
RG-002 | Progress by Zone / Trade | Construction Manager | Actual % and quantity; reasons for variance; action owner; due dates | Confirm progress narrative | AI guessed missing cause or progress value | Draft only
RG-003 | Programme & Milestone Risk | Planner / PM | Baseline vs forecast dates; critical path flag; recovery logic | Confirm delay status | Critical path delay not reviewed | Draft only
RG-004 | Submission / RFI Bottleneck | Technical Manager | Status normalization; overdue days; linked programme/commercial impact | Confirm escalation wording | RFI/legal wording may create claim risk | Draft only
RG-005 | Procurement Readiness | Procurement Manager | Delivery forecast; approval/PO status; supplier action | Confirm material risk | Missing forecast delivery date for critical item | Draft only
RG-006 | Safety / Quality Exceptions | Safety Officer / QAQC Manager | Accident/NCR data; overdue actions; red issues | Confirm compliance statement | High-risk safety item unresolved | Draft only
RG-007 | Commercial Health | QS / Commercial Manager | GP, VO, cashflow, cost certified, commitment, risk exposure | Confirm commercial interpretation | GP/cashflow numbers not reconciled | Draft only
RG-008 | Executive Dashboard | Project Director | Top 5 exceptions; required decisions; risk wording; owner/date | Approve for management issue | Any section owner has not reviewed | Ready for internal issue

## 10_Agent_Demo_Notes
Step | Prompt_or_Demo_Note
Plan Mode Prompt | You are not allowed to generate the report yet. First inspect the workbook, identify the sheets, propose a plan, list expected outputs, data quality checks, KPI calculations, charts, and human review gates.
Build Step 1 | Generate a Python script to read all sheets, validate required columns, normalize status values, and create a data_quality_log.md.
Build Step 2 | Calculate KPI/RAG for progress, milestone delay, overdue RFI/submission, procurement delivery risk, safety/quality exception, and commercial health.
Build Step 3 | Generate charts: planned vs actual progress by zone, milestone delay days, RFI aging, procurement delivery variance, and commercial KPI movement.
Build Step 4 | Render a Markdown/HTML monthly report with Director Dashboard, PM Action Summary, QS Commercial Deep Dive, and Review Checklist.
Self-healing Demo | Ask Codex to handle missing Actual % in PRG-006, inconsistent status labels in 03_Submission_RFI, missing due date in RFI-041, and missing forecast delivery in MAT-026.
Human Review Stop | The final output must stop at 'Draft for PM/QS/Director review'. It must not claim the report is approved or issued.

## 11_Demo_Summary
KPI_Area | KPI_Result | Source | Teaching_Moment
Progress Red rows | 2 | 01_Area_Progress!RAG_Status | Exception detection from planned vs actual progress
Progress Data Gap rows | 1 | 01_Area_Progress!RAG_Status | AI must not infer missing Actual %
Critical programme Red milestones | 3 | 02_Programme_Milestones!RAG_Status | Critical path delay logic
Red overdue RFI / submission items | 1 | 03_Submission_RFI!RAG_Status | Approval bottleneck detection
Procurement Data Gap items | 1 | 04_Procurement!Risk_Status | Missing forecast delivery date handling
Safety / Quality Red items | 1 | 05_Safety_Quality!RAG_Status | Exception-based safety / QA reporting
Current GP % | 4.284% | 06_Commercial_Cost!Current_GP_% | Commercial health for Director / QS view
Open Red management decisions | 3 | 07_Risk_Action_Decision!RAG_Status + Status | Report as decision pack